https://mozlearning.etherpad.mozilla.org/instructor-roadmap
https://wiki.mozilla.org/Webmaker/2013plans

3. Powered by a global community of makers and mentors
Metric: # of mentors
3.1 Makers turned into mentors (organize 2+ events or volunteer online)
3.2 Grassroots instructor community established,  like a year round summer code party
3.3 Tools and support to help community make great content and learning projects
3.4 Tools that make it easy to find local  teachers / events / clubs online
3.5 More + better mentor how to guides: step by step guides for local organizing

Things we want to discuss today:

Educator events goals + roadmap
Remo
2013 events goals + roadmap
Website / online infratstructure brainstorm
Plan for merging hacktivity kits + event guides
See: http://zythepsary.com/mozilla/hacktivity/
And: https://webmaker.org/en-US/events/guides/
Physical Kits
Consider: two buckets of hacktivity audiences:
1) for learners/makers
2) for mentors/teachers

Outcomes for today:

Talking points for Chris' meeting, Dec. 6
Proposal for team and resources (Two tier engagment team)

Program committee:
Laura
Michelle
Gunner - Participation Adviser
Chris - Learning Adviser

Now:
Designer / UX person (someone like Kate)
Developer (someone like Atul)
Education Specialist (Doug)

Soon:
Community manager / Copywriter (someone like Lainie or Erika)
Remo manager (Sayak)
Mozspace webmaker hacktivity coordinator (London as a testbed, Fuzzy)

Later:
Partnerships (…?)
Production people

Engagement External Comms Team:

Comms (Matt, Rebeccah)
Product Manager

Remo event model (marry TTT w/ RemoRewards Etherpad)

Resource sprint roadmap
Now:
Clean up goals + roadmap
Discuss new team roles + resourcing with Mark
Budgeting for Remo
Scouting and invites for Remo event
drawing of the envisioned platform/discussion
Q1:
New team members in place?
Remo Training Event + Hacktivity Sprint
Hive PD Event + Hacktivity and Project Sprint
Contribution pathways v2.0 (submit hacktivities)
interim solution hacktivities on event guide pages
Wireframes + user stories for event/hacktvity kits = the platform, inc. editable and localizable
Q2:
2nd Educator/Remo Hacktivty Sprint (+ all hands?)
Tee up SCP
Communication channels for communities (maybe groups on BSD or Remo)
design and build the event/hacktivity kit maker platform
Q3:
SCP
Q4:
Mozfest

Work week idea for event kit + hacktivity platform

Things we want to discuss soon:

Outreach ideas
curriculum in formal learning (Bischofswerda and Willem de Kooning)
musuem exhibit
unMOOC (Educational Technology w/ Alec Courso)
Mozspaces
"What Every Techie Needs to Know About Education" http://www.third-bit.com/educate/index.php?title=List_of_Articles
Messaging Channels for Educators
Contribution pathways online

Target participants:

Concentric circles:
Already teaching digital literacy, but not yet webmaking
i.e. Educon
NWP
NESTA
certain Hive Members
Coder Dojo
DML folks
Already teaching webmaking
Remos
SCP organizers
Coder Dojo
Experienced webmaker teachers - "mentors"
Already webmaking but not teaching
Remos
Ignite Developers
Popcorn developers
open evangelists

## Mozfest 2012 Wrap Up

* Webinar:

--> Michelle organize
--> Gunner to MC and arrange agenda

    * How did it go
    * How you can get involved
    * What's next

* Report:
    * floor layout
    * quotes
    * outcomes

* 1-pager: what's it like at mozfest
    * public-facing
    * co-written between Gunner + Michelle

## 2013 Event Plans, including leadership model

* Flesh out 2013 events, inc. leadership model
* Map comms + engagement team tiers / roles
* Respond to: 3. Powered by a global community of makers and mentors
    * https://wiki.mozilla.org/Webmaker/2013plans

## Big Picture

Vision:
Long term goal:

Top Level Goals:

Events: in 2013 we want events to be:
*
*
*

Ops: in order for this vision of Webmaker events to succeed we need to:
*
*
*

We need to a strategy to grow participation between Mozfest + Summer Code Party and to sustain webmaking action all year round.

The key to this is working with local "hacktivator" communities to:

* Develop, test and localize hacktivity kits
* Plan and carry out outreach campaigns, including Summer Code Party
* Grow mentorship and training programs building up to SCP and Mozfest

We also need to build in:

* Recognition of achievement (badges)
* Community communication platform (groups on webmaker.org website)
* Celebration (incentive structure, inc. travel to Mozfest)

The details:

## Events:

* 3 regional events (Cluj, NYC, BA, India)
    * codesign + test kits
    * localize tools and messaging
    * plan mentoring outreach and SCP
    * bonus: all-hands co-located with at least one regional event
* Summer Code Party
    * more themes
    * more heterogenous
* annual Mozfest
* Event platform
* Strategic event consultation for other Mozilla programs (i.e. Source Conf, Popcorn Hack Days)

## Mentoring

* By Q1: 100 sign-ups in each region (300 total)
* By Q2: 300 events organized by these mentors.
* BY Q3: 900 newbies + 300 mentors. Each mentor trains up 3 more people, who organize events
* By Q4: 300 mentors come to Mozfest

* Badges
* Website (maybe use Remo?)
* Comms Platform

* Skilled in basic webmaker tools: Popcorn, Thimble, Hackasaurus
* Plus additional specialties: News, Film, Learning, etc.
* Heuristic on what makes a good webmaker leader
* Ownership in planning process

## Hacktivity Kits

* short CTAs (a la Sparked)
* community task board.
* event kit + hacktivity platform v2.0
    * editable
    * localizable
    * modular
* self-service

## Team

* Community Manager (_?)
* Hacktivate (Laura - kits, Chris - Hive)
* Participation Architect (Gunner)
* Comms (Matt, Reb, new copywriter)
* Remo (Fuzzy, Sayak)
* Dev/Designer (someone like Kate Hudson)
* Partnerships (…?)

## To consider

* QA
* Localization
* Press/PR?
* Product Marketing?